## Project Planner
Black Academics Advancement Programme (BAAP) Template: Project Schedule/Work Breakdown Structure (WBS)
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | MONTHS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
| Activity 01 | 1 | 5 | 1 | 4 | 25%
| Activity 02 | 1 | 6 | 1 | 6 | 100%
| Activity 03 | 2 | 4 | 2 | 5 | 35%
| Activity 04 | 4 | 8 | 4 | 6 | 10%
| Activity 05 | 4 | 2 | 4 | 8 | 85%
| Activity 06 | 4 | 3 | 4 | 6 | 85%
| Activity 07 | 5 | 4 | 5 | 3 | 50%
| Activity 08 | 5 | 2 | 5 | 5 | 60%
| Activity 09 | 5 | 2 | 5 | 6 | 75%
| Activity 10 | 6 | 5 | 6 | 7 | 100%
| Activity 11 | 6 | 1 | 5 | 8 | 60%
| Activity 12 | 9 | 3 | 9 | 3 | 0%
| Activity 13 | 9 | 6 | 9 | 7 | 50%
| Activity 14 | 9 | 3 | 9 | 1 | 0%
| Activity 15 | 9 | 4 | 8 | 5 | 1%
| Activity 16 | 10 | 5 | 10 | 3 | 80%
| Activity 17 | 11 | 2 | 11 | 5 | 0%
| Activity 18 | 12 | 6 | 12 | 7 | 0%
| Activity 19 | 12 | 1 | 12 | 5 | 0%
| Activity 20 | 14 | 5 | 14 | 6 | 0%
| Activity 21 | 14 | 8 | 14 | 2 | 44%
| Activity 22 | 14 | 7 | 14 | 3 | 0%
| Activity 23 | 15 | 4 | 15 | 8 | 12%
| Activity 24 | 15 | 5 | 15 | 3 | 5%
| Activity 25 | 15 | 8 | 15 | 5 | 0%
| Activity 26 | 16 | 28 | 16 | 30 | 50%